## Deliverables
Deliverables Sheet
Date: | 28 feb 2017
Priority |  | Task Description | Person Responsible | Complete By: | Comments
Stock Sim
|  | update javadoc, inline documentation | Hui | 2017-03-06
|  | update uml diagram | Hui | 2017-03-06
|  | Move all public instance variables to private | Hui | 2017-03-06 | add set/get methods as needed
|  | Incorporate Dates and validation | Hui | 2017-03-06 | This item might be secondary to performance data
|  | Performance data Turn Summary | Hui | TBD
|  | Performance data Overall Summary | Hui | TBD
|  | Index performance(ie tsx, randomly generated) |  | TBD
|  | Command Line Options |  |  | gui, load data, not required
|  | Game Options |  |  | implement here access with gui
Stock Class
|  | update javadoc, inline documentation | Bob | 2017-03-06
|  | update uml diagram | Bob | 2017-03-06
|  | error codes/messages on stockscraper | Bob/Jason? | 2017-03-06
|  | individual stock performance data | Bob | 2017-03-06
Player Class
|  | update javadoc, inline documentation | Jason | 2017-03-06
|  | update uml diagram | Jason | 2017-03-06
Load Save Class
|  | update javadoc, inline documentation | John | 2017-03-06
|  | update uml diagram | John | 2017-03-06
|  | Integrate into Stocksim and Gui | John/Hui | 2017-03-06
GuiWrapper Class
|  | update javadoc, inline documentation | Jason | 2017-03-06
|  | update uml diagram | Jason | 2017-03-06
|  | Splash Screen (pic or animation)? |  | TBD
|  | Lists for pulldown menu |  | TBD
|  | Load List of Stocks |  | TBD
|  | warning dialogs |  | TBD
|  | Move to Inheritance based model |  | TBD
|  | Performance graph |  | TBD
|  | Incorporate witty messages, fun elements |  | TBD
|  | Player Instruction screen |  | TBD
Overall
|  | Check for privacy leaks |  | 2017-03-06
Go through all TODO tags and update or discard
Identify where exceptions are required
|  | Pick Demo time and date for week 10 | Jason |  | Send out email – need responses
|  | Organize everything in a package | volunteer?
|  | Code Review for Week 10 | 2 people |  | look for encapsulation, coding standards, documentation,
|  | Compile and ensure code is running | volunteer |  | after confirmation, no changes to code at this time until demo
Everyone should get familiar with the guiwrapper and Stocksim class and how they interact
Ideas to implement?
What would make this more enjoyable to use
Game Over (put players in rank compare to someone?)
Options, random events
Random mode
|  | add bonds class? |  |  | probably not at this point
|  | add dividends? |  |  | Possible but maybe too much complexity for end of semester
|  | Stock Qty |  |  | Possible but maybe too much complexity for end of semester
Final Package and submission
Final Review
|  | Readme file |  | Week 13 | Includs how to run and compile description of project
|  | Final Submission |  | Week 13 | zip file, submit to D2L
|  | 7.2 (Friday - team): Graphical User Interfaces (GUI) | volunteer?
|  | 8.1 (Wednesday- team): Arrays | volunteer?
|  | 8.2 (Friday - team): Inheritance | volunteer?
|  | 9.1 (Wednesday - team): Overriding | volunteer?
|  | 9.2 (Friday - team): Polymorphism and abstract classes | volunteer?
|  | 10.1 (Wednesday - team): Interfaces | volunteer?
|  | 11.1 (Wednesday - team): Exceptions | volunteer?
|  | 11.2 (Friday - team): Text files | volunteer?
|  | 12.1 (Wednesday - team): Tracing recursion | volunteer?
|  | 12.2 (Friday - team): Writing recursive methods | volunteer?

## Project Week Milestones
Week 8
Task 1: Identify all privacy leaks due to objects being returned or passed as references in your code. For each, indicate if this privacy leak is intended or should be fixed.
Task 2: Remove all unintended privacy leaks and create a design for a GUI for your game. (Design only, no implementation.)
Week 9
Task 1: Update your design to incorporate inheritance where appropriate. Provide classes that implement the GUI interface you designed last week. For this task, the GUI does not have to respond to user input. Consider the following as a possible design for your project.
Task 2: Have the GUI respond to user input. This can be simply echoing what the user provided as input. Note that you are required to complete a fully functioning application for demo 3 next week.
Week 10
No project milestones due during class this week. You are required to meet with the course instructor this week for demo 3. You will have been assigned a time. You may use the Monday lecture and Monday/Tuesday tutorial to prepare for this demo. Your application should be fully functioning with a graphical user interface.
Bring a (fully charged) laptop containing the code for the project to your demo. Make sure that
You're code is fully functioning. If you continue working on your project one or two days before you demo, make sure you save a working version. You can use this working version for your demo if you introduce a bug at the last minute (which invariably happens at the last minute.)
Your application contains a GUI: all interaction with the user should be through a GUI using event based programming.
Your implementation appropriately uses inheritance, polymorphism and encapsulation.
You bring a hard copy of a class diagram of your implementation. Your diagram should clearly show the classes, relationships between classes, the instance variables and all public methods you created for your project.
Your code is easy to read by using Java coding standards and use Javadoc to document classes and method and in-line documentation where needed. All methods should fit on a single (laptop) screen.
Demoes
Your team will have been assigned a 30 minutes timeslot to do your demo. (See Project -> Week9 for more detail.) During the demo, I'll ask you to compile and run your application on your laptop. If you can't bring a laptop, make sure to e-mail me your code at least 24 hours in advance. I will then ask questions of individual team members. The questions will give me a better understanding of the design of your application and code and will also show me the understanding of individual team members. The team component of the demo will be marked using the following criteria:
Code compiles and runs (1 mark).
Application has full functionality (1 mark).
Classes are organized in packages (1 mark).
Class diagram is complete (1 mark).
Logic and gui code is in separate classes (1 mark).
Class design makes good use of inheritance, polymorphism and encapsulation(1 mark).
Code is well designed and legible (1 mark).
Code is well documented (including Javadoc) (1 mark).
Your individual mark for the demo depends on how well you answer questions.
1/4 if you can ID the code that relates to the question.
2/4 if you can explain the code related to the question.
3/4 if you are able to answer the question.
4/4 if you answer the question clearly and thoroughly.
I usually start with basic questions and, time permitting, will also ask more challenging questions. I will mark the question you answer best.
Week 11
Task 1: Ensure classes are abstract where appropriate or changed to interface where possible.
Task 2: Fix any issues identified during last week's demo. Pay special attention to OO design, coherence of classes and avoidance of code duplication.
Week 12
Task 1: Use files to save the current state of your application and to load a previous state of your application.
Task 2: Ensure you application manages exceptions appropriately. Exceptions should be thrown by all methods except those that can interact with the user directly through the GUI.
Week 13
On Monday: Time for your team to work on your project
On Wednesday:
By 10am: Submit the final version of your project using D2L dropbox. The rubric used to grade this submission is available with the dropbox folder. Your submission must include:
A zip file containing the .java files for your code including the appropriate folders for the packages.
A readme file that indicates how to compile and run your project. (This information can also be included as a comment with your submission in the dropbox.)
A class diagram containing all the classes in your project with relationships between classes. If a class extends a class from the Java library, include that Java library class in your diagram as well.
During the lecture:
Interactive Demo: All teams will demo their project at the same time for the entire class. You must rotate the following tasks among your team members:
Demonstrator: this team member will run and explain your application so others can learn about the functionality of your application. Bring a laptop that will allow you to do this demo. If your team does not have access to a suitable laptop, let the instructor know asap to ensure arrangements can be made.
Architect: this team member answers questions about your project posed by your class mates and possible visitors to the classroom. Bring a hard copy of your class diagram to aid in answering questions and show the design of your system. Also bring a sign that clearly shows your tutorial section, group number and project title.
Investigator: this team member visits stations set up by other teams and learns about applications they created. Each team member will be assigned a set of applications to investigate and provided with questions to answer about each of these applications. A form for each team member with applications to investigate will be provided at the start of class.
Your team will submit the forms filled out by the investigators by the end of the lecture. Your team will be graded on how well the demoes showed the functionality of your application (1 mark), the quality of the class diagram displayed (1 mark), the quality of answers provided to questions (1 mark) and the quality and completeness of the investigations (1 mark).
Cookies and juice provided!
By the end of the day:
Grade distribution: By the end of the end, respond to my e-mail requesting your evaluation of your team members. I will use these submissions to adjust project grades.
Submit your reflective piece. It should address:
what you have learned in the course,
what you've learned from the project,
what you've learned from your team members, and
what you have contributed to the team.
You may choose any format you wish: an essay, poem, painting, video, flow chart, point form document or any other format. If your reflective piece is physical rather than electronic, please submit during the lecture. Your grade will be based on the quality and honesty of the reflection you submit rather than the amount you have learned or contributed. Do not focus exclusively on technical skills you've learned over the semester. In fact, if you feel you've learned very few technical skills or you do not find those skills valuable, do not include technical skills at all in your reflection! A more detailed rubric can be found with the D2L dropbox.